## Wrexham Highways
Project: | St Mary's Avenue, Overton
App No: | P/2023/0186
KMBC Highways Consultation Dated: | 31st July 2024
Wrexham Highway comments
No. | Wrexham Highways Comment | Mode Initial Response / Action (20/08/24) | Mode comments 03/09/24 | Pickstock Homes Notes
1 | • Turning movements for a refuse vehicle at the internal junction within the site. The same revisions two Vehicle Tracking drawings (Ref: PSH06-013-C-Vehicle Tracking (Refuse).pdf and Ref: PSH06-015-B-Vehicle Tracking (Pump Station).pdf) have been provided as were reviewed for the June response. This issue has not been addressed. | Turning movements for a refuse vehicle at the internal junction (by Plot 38) were shown in Mode's Technical Note (dated 24/08/24). It is not clear if Highways have seen this analysis - in any case, the swept path analysis can be undertaken again for the latest layout at this internal junction and turning heads. Action: Mode will update the swept path analysis for the latest layout. | updated turning heads are shown on the attached drawing which requires no overrunning of vehicle bodies | site layout 1522-sit-P01 rev Q has been updated inline with these commnets.
2 | • Confirmation of refuse colection arangements for Plots 11-16 and 43-45 with additional vehicle tracking, if necessary. The same revisions two Vehicle Tracking drawings (Ref: PSH06-013-C-Vehicle Tracking (Refuse).pdf and Ref: PSH06-015-B-Vehicle Tracking (Pump Station).pdf have been provided as were reviewed for the June response. Swept paths indicate the vehicle bodies swinging over the footway which isn't acceptable. The southernmost area of the site is not shown on the plan either. This issue has not been addressed. | BCPs shown on latest plan to serve these dwellings. It will need to be shown that the location of the BCP complies with max distance residents/ collectors can move bins as defined by standards - Mode to review and advise. Swept path analysis will show that a refuse vehicle can access each BCP (addressed as part of point 1). Action: Mode to advice Pickstock re. BCP locations. | bin collection point for 45-46 shown on attached drawing
3 | • Revised vehicle tracking for a 12.25m tanker associated with access to/from the pumping station and modification to the proposed access. The same revisions two Vehicle Tracking drawings (Ref: PSH06-013-C-Vehicle Tracking (Refuse).pdf and Ref: PSH06-015-B-Vehicle Tracking (Pump Station).pdf have been provided as were reviewed for the June response. Swept paths indicate the vehicle bodies swinging over the footway which isn't acceptable and do not show routing through the full site. This issue has not been addressed. | Access to the pumping station has been widened (compared to the layout originally submitted). Swept path analysis can be undertaken to shown that a tanker can access safely. Action: Mode will undertake swept path analysis for a tanker. | updated turning heads are shown on the attached drawing which requires no overrunning of vehicle bodies - potential argument to make that overruning is acceptable for the low frequency of the vehicle, however small increase has been shown to work
4 | • Revised plans to include wider footways to the exterior of Plots 17-21 and Plots 41 and 42. Revised site layout plan (Ref@1522-sit-P01 rev N) shows updated plot numbers so what were Plots 17-21 on rev E are now Plots 18-22 on rev N. It is noted that although the layout of parking and footways/paths has been revised the footway width does not appear to have been widened. Also, the footpath between plots 18 and 19 (previously 17 and 18) has been mostly removed. On rev N plots 18 – 21 have reduced access (no footways/paths) to what was previously proposed. Plots 41 and 42 on rev E are Plots 42 and 43 on rev N. There does not appear to be any footway widening. Footway widths of 2m are required where there are residential units on the frontage on all roads that the developer wishes to be adopted. This issue has not been addressed. | Latest layout looks to have been updated to provide wider footways by the Plots identified by Highways. |  | Site layout 1522-sit-P01 rev P has been updated inline with these commnets.
5 | • Revised plans to indicate 0.6m service strips where no footway is provided. It is not clear if 0.6m service strips have been provided. This issue has not been addressed. | Service strip appears to be indicated adjacent to the carriageway between Plot 33 and pumping station. This looks to be adequate but will be checked by Mode. Action: Mode to check service strips. | 0.6m service strips shown on the attached drawing where required | layout revised.
6 | • Confirmation of proposed street lighting There has been no street lighting information provided. This issue has not been addressed. | Action: street lighting consultant to advise on requirements. |  | Streetlighting design has been done, drawings and calculations to be circulated.
7 | • Clarification of ‘focal point’ and internal site junction denoted by hatching in drawing PSH06- BET-B-013-C. Clarification on interaction between the focal point feature and the driveway to Plot 33. It is noted that the ‘focal point’ has been removed (in rev N) and amendments have been made to Plot 34 (Plot 22 in rev E) including a boundary wall. As per Manual for Streets standard the boundary wall should not exceed 0.6m in height to ensure small children can be seen by drivers. Clarification is required for the proposed wall heights. | Latest layout indicates that feature wall will have a maximum height of 0.6m, as requested. |  | site plan updated
8 | • Revised visibility splays accounting for the proposed landscape layout and siting of trees. Revised visibility splays have not been provided. This issue has not been addressed. | Action: Mode to review forward visibility along access road and at private drives. | forward and junction visibility splays are ok on attached drawing. Trees shown to be removed where potentially impacting visibilty at driveways | site plan updated
9 | • Revised plans showing the proposed pedestrian link to Public Footpath 17 from the northern boundary of the site and alignment of Public Footpath 18 in relation to the development site. Revised plans showing this have not been provided. This issue has not been addressed. | Latest layout appears to show the proposed pedestrain link to PF 17. Action: Mode to review pedestrian link | indicative surfaced route shown on attached drawing to be checked and added to site plan. | au unsurfaced footpath is proposed due the proximity of the existing oak tree.
10 | • Justification for the parking shortfall associated with 3-bedroom properties with only two spaces and measures to manage potential overspill parking. Whilst some of the house types have changed between rev E and rev N which means that some of the parking requirements have been fulfilled plots 35-37 are 1 car parking space short of what would be required each. This issue has not been addressed. | Two visitor spaces at Plot 35-37 have been added. This can be presented to Highways, together with argument that these are smaller 3-bed dwellings. Action: Mode to present case for parking provision to Highways. |  | two visitor spaces have been added for these plots, as they are grouiped and relatively small stater dwellings could a relation in parking standards be accepted.
11.1 | • Long lengths of dropped kerbs alienate the frontage for overflow or visitor car parking | Action: Mode to review long lengths of dropped-kerb | A high parking provision has been applied which will reduce the potential for any overflow parking. Where possible tandem parking has been used to reduce the length of dropped sections. The layout includes sufficient areas for on-street visitior parking.
11.2 | • The visibility from the driveway for Unit 1 is not acceptable due to the location of the high level fence for No 2 Clerc-Y-Mendy which will restrict visibility from the drive onto St Mary’s Avenue | Driveway at Plot 1 relocated to improve visibility. |  | The layout plan has been revised to deal with these commnets moving the parking for plot.
11.3 | • There are concerns over driveway alignments, driveways should be accessed at 90 degrees to the footway to ensure adequate visibility is provided. This isn’t the case for the driveways for units 4, 5,6, 33, 7, 8, 9, 10, 23. | Latest layout shows driveways at 90 degrees. Action: Mode to review driveways. | where possible changes should be made to the allignment of plots 4,7 & 33, remaining plots are within 10 degrees of 90 which is considered acceptable | spays have been added to drives for plots 4, 7 & 33 to assist access.
11.4 | • There are no indications of refuse storage within each plot, there is a concern that the bins may block footways or parking spaces due to the lack of access to the rear gardens, also clarification of bin collection arrangements required for Plots 44-46. WCBC may decline to access private roads and vehicles will not reverse further than 12m and there is a maximum distance of 15m for operatives or residents to walk moving bins. | Action: Pickstock to advise on bin storage location at individual dwelling. BCP at Plots 44-46/ private rpads addressed by point 1 and 2. | access to rear gardens needs to be shown for plots 2,4,7,8,9,23,24,25,26,27,28,29,30,31,32,33,34,39,42,43,44,45,46 | Bins will be stored in rear gardens and brought to the roadside by house holders on bin collection days. Bin stores has been indicated for plots 10-13. Bin collection points have been shown where dwellings do not front onto the adopted highway. Gates will be provided into rear gardens.
11.5 | • Swept paths of a 7m long (medium sized) delivery vehicle should be provided in the turning head proposed outside unit 46 | Action: Mode to undertake requested swept path analysis | swept path shown to work on the attached drawing
11.6 | • Parking provision for units 35-37 falls short of the WCBC which states that three car parking spaces should be provided for each three bedroom dwelling, therefore this has the potential to cause overflow parking on the busiest stretch of the site access road | Will be addressed by point 10.
11.7 | • The access to plot 23 is not acceptable, its exceptionally narrow and accesses at an oblique angle restricting visibility on safety grounds | Action: Mode to review revised access arrangement at Plot 23 (and parking at Plot 24). | proposed changes to the turning head should address this problem
11.8 | • The parking space allocated to plot 22 closest to plot 23 is not acceptable as it results in reversing over the length of the existing footway, and this footway is required to be 2m wide to meet adoptable standards where there is residential frontage access | Latest layout shows a revised driveway which looks acceptable. |  | The layout plan has been revised to deal with these commnets.
11.9 | • The same issue for the eastern most parking space for plot 24, results in reversing extensively over the footway, where the building line of plot 24 restricts visibility which compounds the safety issue | Action: Mode to review revised parking spaces at Plot 24, 41 and 42 | proposed changes to the turning head should address this problem
12 | • The same issue for the driveway for unit 41 |  | fixed on latest layout
12.1 | • The same issue for the driveway for unit 42 |  | fixed on latest layout
12.2 | • As stated previously the footway widths are not acceptable, and there is no footway infront of plots 18 and 19, this is not acceptable on pedestrian safety grounds | Addressed in latest layout
12.3 | • A service strip is not acceptable where there is residential frontage access, a 2m footway is required infront of units 25 to 29 | Addressed in latest layout
12.4 | • WCBC does not accept garages as parking spaces | Action: Mode to review parking provision and use of garages
12.5 | Driveway dimensions are required to be 5m wide for double driveways, and 10m length for tandem parking (1 car behind another) or 15m length for three cars (1 behind another). Driveways should also be 0.5m longer if a garage requires to be accessed. The driveway dimensions are short of these standards across the site | Action: Mode to review driveway dimensions |  | parking spaces have been updated to comply.
12.6 | • The footway is required to be 2m infront of units 42 and 43 | Addressed in latest layout |  | The layout plan has been revised to deal with these commnets.
12.7 | • The refuse arrangements for units 44-46 are required to be clarified to comply with WCBC standards, is this proposed to stay a private drive? There is no footway, no service strip and no street lighting. | Action: Pickstock to staying a private road BCP at Plots 44-46/ private rpads addressed by point 1 and 2. |  | will be a private road / drive with bin collection point provided at road entrance.
12.8 | • There is still no clarification on a ped/cycle link through to Clerc-Y-Mendy | No link proposed |  | Agreed, no link requested or proposed.
12.9 | • Swept path of a large car turning and exiting plot 34 in forward gear is required | Action: Mode to undertake requested swept path analysis for car at Plot 34 | as with all drives for 3 cars, vehicles are expected to drive on and reverse off, remove the turning area shown and potentially move the marked spaces closer to the road | layout revised.
13 | • Pedestrian access for units 35 to 37 need amendment as there is no clear pedestrian access if cars are parked on the spaces shown | Latest layout shows ped access route. Action: Mode to review ped access arrangement | access shown | layout revised.
13.1 | • The footprint of plot 3 blocks visibility from the drive as there is no set back from the footway | Latest layout shows ped access route between ddriveway and building, which may provide adequate visibility. Action: Mode to review. | dwelling may need to be set back a further 200mm to accommodate pedestrain visibilty splay, shown on attached drawing | dwelling moved 200mm.
13.2 | • There are concerns regarding visibility from plot 10’s car parking space, can the applicant clarify if that is fencing shown around the space | Latest layout shows amended fence line to improve visibility. Action: Mode to review | can fence line be cut back slightly further on the eastern side as shown in the attached drawing. | fence revised on site plan
13.3 | • The footways for units 20-21 are not adequate as if cars are parked in the spaces there isn’t a clear route through. | Latest layout shows amended footways. Action: Mode to review | fixed on latest layout | layout revised.