| Ysgol yr Hafod Johnstown – Safe Routes to School 2021-22 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Data taken from the Travel Plan by Wynne Construction Most Recent Data: (Autumn 2019) (Data will be updated following Eco council Survey- November 2021) Survey of students across the two school sites has been undertaken to consider the way in which they currently travel to that school. Out of a total of 317 pupils who responded: - 186 stated they travelled by car, which was 58.5% of the total - 119 stated they walked to school every day, equating to 37.5% - 0 stated they travel to school by bus, equating to 0%, - The remaining 12 stated they cycled to school, equating to 4% Desired Outcomes: The following targets are initially being set to assess the success of the Travel Plan: - On opening – 41.5% of pupils by sustainable travel modes; - Within 1 year of opening – 43.5% of pupils by sustainable travel modes; and - Within 3 years of opening – 45.5% of pupils by sustainable travel modes. |  |  |  |  |  |
| Active Travel Plan Area | Actions to be taken | Person responsible | Timescale for completion | Monitoring | Review/ Next steps |
| Obtaining Information | - Eco Council survey to obtain a more recent and detailed baseline data on the current situation regarding travel to/from school - Revise the targets for increasing the number of families actively travelling to/from school based on the most recent survey | SMT Eco council | October/ November 2021 |  |  |
| Pupil Involvement | - Eco council to devise survey to find out about travel to and from school - Video to promote the survey and active travel - Eco council traffic crew to monitor and promote safe parking and active travel to school. - School council to write to residents and parents to promote positive relations and ‘good neighbours’ within the community. - Eco council launch competition for Walking to school posters - Eco council ask all classes to make posters for residents to put in windows regarding safe and considerate parking. - Bike/ Scooter hire- to promote active travel – possibly acquire funding from WG Active Travel for this - Class topics on climate control / reducing pollution and the benefits of walking. - Road Safety assemblies on a termly basis | SMT Eco council School Council Eco council Class Teachers | October/ November 2021 January 2022 January 2023 Ongoing |  |  |
| Sustrans Initiatives | - Safe routes to school activity for Key Stage 2. Children to plan and map routes to school. - ‘Be Bright/ Be Seen’ session - children wear fluorescent clothing to school to promote safety during the winter months. - Active Travel weeks each term to promote walking/biking or scooting to/from school - Annual Sustrans Campaign’ Big Walk and Wheel’. National competition to get school with highest numbers travelling actively to/from school - Scooter skills and balance bike day - Doctor Bike day - Bike maintenance for Upper School | Sustrans Officer Sustrans Officer/SMT | October 2021 November 2021 Termly March 2022 Summer term 2022 |  |  |
| Staff | - Encourage staff who live within 1 mile of the school to actively travel to/from school - For staff living further than 1 mile, consider ways to possibly park and stride to school - Where possible, staff to car share to limit the number of cars on site | All Staff | January 2022 |  |  |
| Traffic Management (During decant) | - Staff and Eco Council set up a traffic patrol at the end of the school day to promote active travel and considerate parking. - Decant to FP - SLT members on traffic duty to support parents in safe parking. - Poster and social media campaign to promote walking to school. - Use of Bowling green car park to create additional parking for staff during the decant. - Use of multiple entrances across the FP site to spread families across the school and reduce congestion. - Governors consult to amend school session times at the end of the day to reduce amount of time parents are waiting for FP and KS2 | SLT/ Eco council SLT Governors/HT | January 2022 January 2022 October- December 2021 |  |  |
| Traffic management (New Build) | - Use of multiple entrances across the site to spread families across the school and reduce congestion - Set up a walking bus to promote children walking to school. Staff members walk children to school from an agreed drop off point. - Eco Council to promote active travel to school - Improved bike shelter facilities on site with lighting. - New entrance onto site from Ruabon road. - Bike Ability sessions for Year 5 and 6. - Kerbcraft sessions for Upper Foundation Phase pupils - Maintain entrance/ walkway from Heol Offa onto school site. |  | From January 2023 |  |  |