## Sheet1
Compliance
Wrexham DO |  |  |  | Pre- Commencement
CONDITIONS TRACKER |  |  |  | Pre- Occupation
WRRP/2020/0598 |  |  |  | Post Occupation Management
2021-01-08
No. | Topic | Condition | Timing | Responsibility | Submission Date | Decision Date | notes
1 | Compliance | The development hereby permitted shall be commenced before the expiry of five years from the date of this permission. Reason: To comply with Section 91(3) of the Town and Country Planning Act,1990. | Compliance | N/A | N/A | N/A | N/A
2 | Compliance | The development shall only be carried out in strict accordance with the details shown on the approved drawing(s) numbered SL_P20020_DWG-0_ EX00P2 Location Plan EX01P4 Existing site plan EX10P3 Existing ground floor EX11P2 Existing first floor EX12P2 Existing roof plan EX30P3 Existing elevations EX31P2 Existing elevations PR01P10 Proposed site layout PR10P6 Proposed ground floor PR11P2 Proposed first floor PR12P5 Proposed roof plan PR20P5 Proposed sections PR21P2 Proposed sections PR30P4 Proposed elevations PR31P4 Proposed elevations PR32P2 Street view WRDO-MMD-XX-00-DR-D-0001 P01 Indicative drainage3700P2 External lighting and as contained within the application documentation. Reason: To comply with section 71ZA (2) of the Town and Country Planning Act1990. | Compliance | F+G | N/A | N/A | Noted
3 | Compliance | No facing or roofing materials shall be used other than those detailed on the application form and within the approved application documentation. Reason: To ensure a satisfactory standard of appearance of the development in the interests of the visual amenities of the area in accordance with PoliciesGDP1 and PS2 of the Wrexham Unitary Development Plan. | Compliance | F+G | N/A | N/A | Noted
4 | Pre commencement condition(s) | No part of the development shall commence until an appropriate Dust Management Scheme has been submitted to and approved in writing by the Local Planning Authority. The dust mitigation measures as are approved shall be fully implemented for the entire duration of the construction phase. Reason: To protect the amenities of the occupiers of nearby properties in accordance with Policy GDP1 of the Wrexham Unitary Development Plan. | Pre- Commencement | Principal Contractor. | 2021-01-27 | TBC | The Principal Contractor has provided the Dust Management plan which has been reviewed by the Principal Designer and issued to Simon Greenland (planning officer) to discharge condition 4 along with condition 8.
5 | Pre commencement condition(s) | No development shall take place until a phased site investigation of the nature and extent of contamination has been carried out and submitted to and approved inwriting by the Local Planning Authority. If any contamination is found during the site investigation, no part of the development shall commence until a scheme specifying the measures that will be taken to remediate the site to render it suitable for the development hereby permitted has been submitted to and approved in writing by the local planning authority. The site shall thereafter be remediated in accordance with the approved scheme. If during the course of development any contamination is found that has not been identified in the site investigation, no further development shall take place on those parts of the site where that contamination has been found until an additional scheme of remediation has been submitted to and approved in writing by the local planning authority for those parts of the site. The relevant parts of the site shall thereafter be remediated in accordance with the additional scheme of remediation. Reason: To safeguard the amenities of the adjoining properties | Pre-Commencement | Mott MacDonald | TBC | TBC | Ground investigations were undertaken at design stage and the report provided to Simon Greenland (planning officer) on the 22/01/21. The ground investigations identified the presence of slightly elevated levels of hydrocarbons from 2 samples taken from the footprint area of the extension. Due to the location of the sample and gradient of the car park we do not believe the source of contamination is from the Royal Mail site. Any spoil from the foundations will be disposed of under licensed conditions and the contractor will develop RAMS that will be reviewed and signed off by the client retained design team (Mott Macdonald) before works commence. The contaminated ground officer from Wrexham Council has requested the a Contaminated Land Risk Assessment is undertaken to discharge the condition. Motts have been instructed and the report should be ready by the 05/02/21. The application to discharge will be submitted separately to 4 & 8.
6 | Compliance | Each part of the site subject to the remediation under the scheme(s)approved as part of condition 5 shall not be occupied/used until a Validation Report has been completed in respect of that part of the site and submitted to and approved in writing by the Local Planning Authority. Reason: In the interests of the amenities of the future occupants of the buildings in accordance with Policy GDP1 of the Wrexham Unitary Development Plan. | Compliance | TBC further to condition 5 agreement. | N/A | N/A
7 | Compliance | The vehicular parking area as shown on approved drawing numbers(s)PR01P10 shall be fully laid out, surfaced and drained prior to first use of the development. This parking area shall thereafter be permanently retained and kept free of any obstruction, and made available solely for the parking of motor vehicles at all times. Reason: To provide for the parking of vehicles clear of the highway in accordance with Policies GDP1 and T8 of the Wrexham Unitary Development Plan | Compliance | Faithful + Gould/RM Operation post completion | N/A | N/A | Note: The operation has signed off the proposed parking layouts. There will be formal handover on completion to ensure the end users understand the planning condition and the parking layout is managed and followed during occupation.
8 | Pre commencement condition(s) | No part of the development shall commence until a Construction Traffic Management Plan including provisions for contractor parking has been submitted to and approved in writing by the Local Planning Authority and the Plan as is approved has been fully implemented. Reason: In the interests of highway safety in accordance with Policy GDP1 of the Wrexham Unitary Development Plan. | Pre- Commencement | Principal Contractor. | 2021-01-27 | TBC | Please refer to RMG Wrexham, Tender Site Layout & Phasing Plan REV B. The Principle Contractor has confirmed that there will be no more than 8 contractors vans on site at any one time.
9 | Pre commencement condition(s) | The development shall be carried out in accordance with the scheme for the comprehensive and integrated drainage of the site set out in the drainage report WRDO-MMD-ZZ-XX-SP-D-0001 and drawing WRDO-MMD-XX-00-DR-D-0001 P01.The scheme as approved shall be implemented in accordance with a timescale to be agreed as part of the SAB process and maintained thereafter. Reason: To ensure that effective drainage facilities are provided for the proposed development, and that no adverse impact occurs to the environment or the existing public sewerage system in accordance with Policies GDP1 andEC13 of the Wrexham Unitary Development Plan. | Compliance | Mott MacDonald | N/A | N/A | Mott MacDonald have been in close contact with the SAB officer during the design stage and will be submitting final proposals for approval on the 22/01/21.
10 | Pre commencement condition(s) | The landscaping scheme approved as part of this application shall be fully implemented in strict accordance with approved drawing no. PR01P10within three months of the first use of the development with the exception of soft landscaping which shall be carried out in the first planting season(November to March) or seeding season (April to September) following the first use. Reason: To ensure a satisfactory standard of appearance of the development in the interests of the visual amenities of the area in accordance with PoliciesGDP1 and PS2 of the Wrexham Unitary Development Plan. | Compliance | Faithful+Gould | N/A | N/A | Noted. F+G will ensure compliance as CA
11 | Pre commencement condition(s) | Planting implemented in accordance with approved landscaping scheme drawing no. PR01P10 shall be retained for a minimum of 5 years. Within this timescale, any planting becoming severely damaged or seriously diseased, or is in poor physiological condition and/or are removed without the written permission of the Local Planning Authority shall be replaced within the next available planting season by trees or shrubs of similar size and species to those originally required to be planted. Reason: To ensure a satisfactory standard of appearance of the development in the interests of the visual amenities of the area in accordance with PoliciesGDP1 and PS2 of the Wrexham Unitary Development Plan. | Compliance | Faithful+Gould | N/A | N/A | Noted. F+G will ensure compliance as CA