## Sheet1
APPENDIX C - SCHEDULE OF REMEDIATION ACTIVITIES AND SUPPORTING RESULTS AND EVIDENCE
Ref. | Evidence/Information Required | Plots | Information Provided | Appendix D Reference | Information References | Test Dates | Report Date | Compliance Requirement | Compliance Note | Deviation
7.1.1 | Pre-placement testing of sub-soil for site-won capping materials | At stockpile | Site won Subsoil material chemical composition (1 sample per 1500m3 for site won soils). Test results provided by ADM Regeneration | D4.1 TO D4.4 | Exova Results Reports: 14/2456/RG/S/C1, 14/2694/RG/S/C1, 14/2847/RG/S/C2, 14/2694/RG/S/C2 | 17.06.14, 03.07.14, 16.07.14, 03.07.14, | 01.07.14, 16.07.14, 24.07.14, 25.07.14 | Material to be compliant with geotechnical and chemical requirements. | Test result show compliance | none
7.1.2 | Inspection of sub-soil capping material and indicator barrier | All | Visual inspections carried out by HLN. Record photographs and notes | D8.1 | Visual Inspection by HLN and trial pit and depth measurement by HLN 15.07.15 for Plots 1,3,4,6,7+8,18,20+21,22+23. Awaiting photo records from the remaining plots from Keepmoat | 15.07.15 | 15.07.15 | Visual compliance in accordance with construction drawings and specifications | Deemed satisfactory by HLN | none
7.1.3 | Sub-soil placement levels | All | As-laid sub-soil capping levels at each stage and final as-laid depths included in site-wide level survey drawing provided by ADM Regeneration | D5.1 TO D5.5 | Comparison between ADM Survey Drawing 10309-006 (14.07.14) and Drawing 10309-007 (26.08.14). | 26.08.14 | 26.08.14 | As-laid recorded site levels must show that 800mm of clean sub-soil capping has been laid in garden areas, 400 in public landscaped areas | Level survey show compliance (TBC) | some very limited areas were 50mm short due to site activities, so topsoil depths were increased to make up the full depth required
7.1.4 | Post-placement testing of site-won capping materials | All | In-situ capping layer material recovered from gardens and tested. Test results provided by E-Geo. | D4.5 | DETS Results Report: 15-40518(22.07.15) | 16.07.15 | 22.07.15 | Material to be compliant with chemical requirements | Test result show compliance | none
7.1.5 | Disposal of unsuitable materials off-site | All | Unsuitable material from excavated made ground (geo-technical and geo-environmental) removed from site. Waste transfer records provided by ADM Regeneration | D3.1 TO D3.3 | Material removal tickets from site for Keepmoat for waste (ASH Alans skips), oversize material (Loweroak) and soil disposal (Loweroak) | generally July 2014 | generally July 2014 | Materials off-site must be recorded, delivered by licenced carrier and disposed of in accordance with legislation | Material movements recorded and deemed satisfactory | none
7.1.6 | CBR testing of capped site | All | Site-wide CBR test results drawing provided by ADM Regeneration | D2.1 TO D2.7 | CBR Location plans by ADM, test results from TestConsult Limited, test report from Murray Rix ref MRN2420 30.07.14 | generally July 2014 | generally July 2014 | CBR test result must be compliant with engineer's requirements | Deemed satisfactory by HLN | none
7.1.7 | Import of granular construction materials | All | Imported construction materials for various surfacing construction activities provided by groundworks sub-contractor | D1.1 TO D1.4 | Material delivery tickets to site for Keepmoat. Imported 6F2 [including recycled and crushed brick) from ASH Alans Skips, Ivor Owens & Sons Ltd, L&D Plant Hire. Imported Clean Stone from Williams Holdings | generally June 2014 | generally June 2014 | Materials imported to be recorded | Material movements recorded and deemed satisfactory | none
7.2.1 | Pre-placement testing of top-soil | All | Chemical and specification report provided by supplier via groundworks sub-contractor | D1.5 | SAL Results Report 475374-1(15.05.15) | 07.05.15 | 15.05.15 | Material to be compliant with chemical and specification requirements | Test result show compliance | none
7.2.2 | Inspection of top-soil material | All | Visual inspections carried out by HLN. Record photographs and notes | D8.1 AND D8.2 | Visual Inspection by HLN | 15.07.15 | 15.07.15 | Visual compliance in accordance with construction drawings and specifications | Deemed satisfactory by HLN | none
7.2.3 | Top-soil placement levels | All | As-laid topsoil depths included in site-wide level survey drawing provided by groundworker | D5.8, D5.9, D5.10, D5.11, D5.12,D5.13 | Surveyed topsoil levels provided by Keepmoat. Also, additional levels proving the depth of placed capping meets the requirements are contained within D5.6 and D5.7 | 27.07.15, 04.08.15 | 27.07.15, 04.08.15 | As-laid recorded site levels must show that 200mm of clean sub-soil capping has been laid in garden areas and in public landscaped areas | Awaiting final data. HLN have observed compliant levels across completed plots as of 28.07.15 | none
7.2.4 | Post-placement testing of top-soil | All | As laid topsoil material recovered from gardens and tested. Test results provided by E-Geo. | D4.5 | DETS Results Report: 15-40518(22.07.15) - all samples marked # T/S | 16.07.15 | 22.07.15 | Material to be compliant with chemical and specification requirements | Test result show compliance | none
7.3.1 | Remediation phase gas monitoring | All | Gas monitoring results provided by E-Geo | D6.1 | Residential Development, Glan Gors, Wrexham – Remediation Phase Gas Monitoring Results. E0500.S3.R1 | 03.05.14 to 02.06.15 | 13.07.15 | Trend recording | Trend recording | none
7.3.2 | Gas protection measures inspection | All | Visual inspections carried out by HLN. Record photographs and notes | D8.3 | Visual Inspection by HLN | 22.10.14 | 22.10.14 | Visual compliance in accordance with construction drawings and specifications | Deemed satisfactory by HLN | none
7.3.3 | Gas installation integrity report | All | Integrity testing and inspection report provided by MEC Environmental | D7.1 | MEC Environmental Report: Gas Membrane Installation, Validation Report, Anthony Eden Drive, Wrexham. 10.06.15 | 22.10.14 to 14.05.15 | 10.06.15 | Confirmation of satisfactory workmanship report and completeness of installation | Installation approved by MEC Environmental | none
7.3.4 | Post construction gas monitoring | BHs | Gas monitoring results provided by E-Geo | D7.2 | Awaiting | Awaiting | Awaiting | Trend recording | Trend recording | none